## Summary
ACCEPTANCE TEST CASES — STATUS SUMMARY
Source: ACCEPTANCE_AND_TEST_CASES.md |  | Total cases: 150
Status | Count | % of total
Pass | 6 | 4%
Partial | 2 | 1%
Fail | 0 | 0%
Blocked | 1 | 1%
Not Run | 141 | 94%
Priority × Status | P0 | P1 | P2
Pass | 4 | 2 | 0
Partial | 1 | 1 | 0
Fail | 0 | 0 | 0
Blocked | 1 | 0 | 0
Not Run | 18 | 89 | 34
Executed (Yes) | 8
Attempted/Blocked | 1
Not executed | 141

## Test Cases
Part | Area | TC ID | Title | Priority | Executed | Status | Run | Test (Steps / Expected) | Result / Notes
1 | - | TC-1-01 | Cold launch smoke | P0 | Yes | Pass | Run 1, after fix | Pre: fresh install, permissions granted. Steps: 1) Launch app. 2) Open each top-level tab/section. Expected: every screen renders without crash; FGS notification present. | launch OK, FGS foreground + notification ✓. Uncovered the ForegroundServiceDidNotStartInTimeException launch crash → fixed in AppLockForegroundService.onStartCommand → re-verified 0 crashes.
1 | - | TC-1-02 | Settings hub completeness | P1 | Yes | Pass | Run 1 | Pre: app open. Steps: open Settings → tap every row (Kid Mode, Multiple Kids, Remote report, Tamper, Appearance, Permissions, Help). Expected: each opens its detail screen and back returns to the hub. | all hub items present; Remote report → role screen → child pane (QR generated) all render, no crash.
1 | - | TC-1-03 | Promo-free reachability | P0 | No | Not Run |  | Pre: promo_active=true. Steps: exercise a premium feature (e.g. Multiple Kids, Themes). Expected: fully usable, no paywall/Plus lock.
2 | - | TC-2-01 | Permission preflight | P0 | No | Not Run |  | Steps: open Permissions dashboard. Expected: every required permission shows granted; revoking one reflects immediately.
2 | - | TC-2-02 | Firestore rules live | P0 | No | Not Run |  | Pre: Firestore enabled. Steps: from the app (child) tap Sync now with sharing on. Expected: "Report uploaded ✓" and a reports/{id} doc appears. (Fails → rules not published / DB not created.) | Never device-tested
2 | - | TC-2-03 | License tester | P1 | No | Not Run |  | Steps: with promo off + paywall on, start a purchase. Expected: Play shows the test-purchase (no real charge) flow.
2 | - | TC-2-04 | Config flip propagation | P1 | No | Not Run |  | Steps: change promo_active in Remote Config, relaunch after fetch window. Expected: app reflects the new value (gating changes).
3 | A. Core app-lock & face authentication (P0) | TC-A-01 | Protected app locks | P0 | No | Not Run |  | Pre: App X protected; face enrolled; service running. Steps: open App X. Expected: lock surface within ~1s; App X content not interactable.
3 | A. Core app-lock & face authentication (P0) | TC-A-02 | Correct face unlocks | P0 | No | Not Run |  | Steps: at the lock, present enrolled face, eyes open, blink. Expected: unlocks; App X usable.
3 | A. Core app-lock & face authentication (P0) | TC-A-03 | Wrong face rejected | P0 | No | Not Run |  | Steps: present a different person's face. Expected: stays locked; no unlock after repeated attempts.
3 | A. Core app-lock & face authentication (P0) | TC-A-04 | Photo/liveness rejected | P0 | No | Not Run |  | Steps: hold a printed/phone photo of the enrolled face. Expected: does not unlock (no blink/liveness).
3 | A. Core app-lock & face authentication (P0) | TC-A-05 | Settings uses LockActivity | P0 | No | Not Run |  | Pre: Settings-lock on. Steps: open system Settings. Expected: full-screen lock (not overlay); covers Settings reliably.
3 | A. Core app-lock & face authentication (P0) | TC-A-06 | Back/Home no bypass | P0 | Yes | Pass | Run 3 | Steps: at the lock press Back, then Home, then re-open the app. Expected: sent Home; app re-locks on re-entry; never shows un-authenticated content. | Realme, Kid-Mode budget lock over Ludo. BACK ×2 → overlay stays up, game not revealed. HOME → launcher (overlay cleared, game not usable). Re-open → watchdog re-asserts the lock overlay. No un-authenticated content at any step.
3 | A. Core app-lock & face authentication (P0) | TC-A-07 | Reboot persistence | P0 | No | Not Run |  | Steps: reboot device; open a protected app. Expected: service auto-started; lock works.
3 | A. Core app-lock & face authentication (P0) | TC-A-08 | Overlay revoked fallback | P1 | No | Not Run |  | Steps: revoke "display over other apps"; open a protected app. Expected: LockActivity path used; no crash.
3 | A. Core app-lock & face authentication (P0) | TC-A-09 | Watchdog re-show | P1 | Yes | Pass | Run 3 | Steps: via fast app-switch try to land on a protected app without the lock. Expected: watchdog forces the lock to appear. | Realme — after dismissing the lock to Home, re-opening Ludo re-armed the overlay every time (the 250 ms monitor-loop watchdog re-asserts it). overlay count flipped 0→1 on each re-entry.
3 | A. Core app-lock & face authentication (P0) | TC-A-10 | Emergency app never gated | P0 | Yes | Pass | Run 3 | Steps: open Phone/Dialer while budget is exhausted / app-lock active. Expected: opens immediately, never locked. | Realme, budget exhausted (used 188 / limit 59) — Phone (com.google.android.dialer) opened immediately, no overlay, never gated. (Allow-listed preset A = Phone + Messages.)
3 | A. Core app-lock & face authentication (P0) | TC-A-11 | Screen off/on during lock | P1 | No | Not Run |  | Steps: at the lock, turn screen off then on. Expected: still locked; auth still required.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-01 | Budget exhaustion locks | P0 | Yes | Pass | Run 3, after fix | Pre: daily limit set (e.g. 30 min), Kid Mode on. Steps: use controlled apps until the budget hits 0. Expected: controlled apps lock; allow-listed apps still open. | Realme, used 188 / limit 59 — Ludo (controlled) locks via overlay even with Shield backgrounded; Phone/Messages (allow-listed) stay open. Uncovered + fixed a P0: the kid-mode lock used a background Activity launch (BAL-blocked on ColorOS after the ~10 s grace window) so nothing displayed; switched to the overlay path. Verified holds. See TEST_RUN_LOG Run 3.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-02 | 07:00 reset | P1 | No | Not Run |  | Steps: exhaust budget; cross 07:00 (or set clock). Expected: budget resets; usage before/after attributed to the correct budget-day.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-03 | Night lock | P1 | No | Not Run |  | Pre: night window configured. Steps: open a controlled app during night hours. Expected: locked; outside the window it isn't (budget permitting).
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-04 | Allowed preset | P1 | No | Not Run |  | Steps: select a preset; open an allowed app and a non-allowed one. Expected: allowed opens, non-allowed gated.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-05 | Custom picker | P1 | No | Not Run |  | Steps: choose Custom, pick specific apps. Expected: only those stay open. (If ALLOWED_PRESETS flipped premium off-promo, Custom is gated.)
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-06 | Free Play session | P1 | No | Not Run |  | Steps: start Free Play for N min. Expected: controlled apps open for N min, then re-lock; a Free Play record is logged; start/end notifications post.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-07 | Budget extension | P1 | No | Not Run |  | Steps: grant +15 min. Expected: today's allowance +15; history shows the grant; next 07:00 zeroes extensions but keeps history.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-08 | Earned time | P1 | No | Not Run |  | Steps: complete an earned task. Expected: the task's minutes are added to the budget.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-09 | Schedule enforcement | P1 | No | Not Run |  | Steps: configure a schedule block. Expected: controlled apps locked during the block.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-10 | Per-app limit | P1 | No | Not Run |  | Steps: set a per-app limit (e.g. YouTube 10 min). Expected: that app locks at 10 min even if total budget remains.
3 | B. Kid Mode — single kid (P1, budget=P0) | TC-B-11 | Auto-block new app | P1 | No | Not Run |  | Pre: auto-block on. Steps: install a new app. Expected: it's auto-added to protected/blocked.
3 | C. Multi-kid — 2 profiles (P1) | TC-C-01 | Enrol two kids | P1 | No | Not Run |  | Steps: enable Multiple Kids; enrol Kid A and Kid B faces. Expected: both stored; selector shows both.
3 | C. Multi-kid — 2 profiles (P1) | TC-C-02 | Correct identification | P1 | No | Not Run |  | Steps: Kid A opens a controlled app. Expected: identified as A; A's budget applies; session attributed to A.
3 | C. Multi-kid — 2 profiles (P1) | TC-C-03 | Sibling ambiguity | P1 | No | Not Run |  | Steps: present a borderline/sibling face. Expected: tap-to-confirm or stricter profile; never a hard lockout.
3 | C. Multi-kid — 2 profiles (P1) | TC-C-04 | Parent override | P1 | No | Not Run |  | Steps: at a kid lock, present the parent face. Expected: unlocks/authorizes.
3 | C. Multi-kid — 2 profiles (P1) | TC-C-05 | Per-kid budget isolation | P1 | No | Not Run |  | Steps: exhaust Kid A's budget. Expected: A is locked; Kid B (under budget) is not.
3 | C. Multi-kid — 2 profiles (P1) | TC-C-06 | Family dashboard accuracy | P1 | No | Not Run |  | Steps: open Family comparison. Expected: each kid's numbers match their actual usage; comparison is neutral/correct.
3 | D. Stats & dashboards (P1; screen-off=P0) | TC-D-01 | No screen-off phantom usage | P0 | No | Not Run |  | Steps: open a controlled app, turn the screen off, wait 15+ min, turn on. Expected: the app's recorded time does not include the screen-off period (the "Clock ~1h59m" bug). Validate on the user's OEM.
3 | D. Stats & dashboards (P1; screen-off=P0) | TC-D-02 | Window consistency | P1 | No | Not Run |  | Steps: compare today vs 7-day vs month. Expected: numbers are plausible and consistent; budget-day boundaries at 07:00.
3 | D. Stats & dashboards (P1; screen-off=P0) | TC-D-03 | Stats gate | P1 | No | Not Run |  | Pre: promo off, BASIC_STATS premium, non-premium. Steps: open Stats. Expected: locked empty state with upsell, not the dashboard.
3 | E. Tamper protection (P1) | TC-E-01 | Anti-uninstall | P1 | No | Not Run |  | Pre: Device Admin on. Steps: attempt uninstall. Expected: blocked; requires removing admin first.
3 | E. Tamper protection (P1) | TC-E-02 | Settings lock | P1 | No | Not Run |  | Pre: settings-lock on. Steps: open system Settings. Expected: parent-face lock required.
3 | F. Monetization (P0) | TC-F-01 | Promo = free, no prompts | P0 | No | Not Run |  | Pre: promo on. Steps: use the app broadly. Expected: no paywall; all features free.
3 | F. Monetization (P0) | TC-F-02 | Billing-unavailable safety | P0 | No | Not Run |  | Steps: disable Play / go offline; launch. Expected: no crash; protection works; treated as free.
3 | F. Monetization (P0) | TC-F-03 | Paywall real prices | P1 | No | Not Run |  | Pre: promo off, paywall on, non-premium. Steps: open paywall. Expected: real monthly+annual prices, trial timeline, Restore, Terms/Privacy.
3 | F. Monetization (P0) | TC-F-04 | Purchase unlocks | P1 | No | Not Run |  | Steps: buy via license tester. Expected: premium granted, acknowledged, cached; premium features unlock.
3 | F. Monetization (P0) | TC-F-05 | Restore | P1 | No | Not Run |  | Steps: reinstall / new launch; tap Restore. Expected: premium restored without re-purchase.
3 | F. Monetization (P0) | TC-F-06 | Lapse reconciles | P1 | No | Not Run |  | Steps: cancel/expire the sub; relaunch. Expected: reverts to free; premium features re-gate.
3 | F. Monetization (P0) | TC-F-07 | Single-feature flip | P1 | No | Not Run |  | Steps: set feature_tiers_json to make only THEMES premium (promo off, non-premium). Expected: only Themes gates; others unchanged.
3 | F. Monetization (P0) | TC-F-08 | APP_LOCK flip (deliberate) | P0 | No | Not Run |  | Steps: flip APP_LOCK premium for a non-subscriber (promo off). Expected: the documented behavior — confirm this is intended, since it can disable protection. Validate consciously.
3 | G. Push notifications — FCM (P2) | TC-G-01 | Broadcast received | P2 | No | Not Run |  | Steps: send a Firebase console message to topic all. Expected: notification appears (app foreground and backgrounded).
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-01 | Pairing round-trip | P1 | Yes | Partial | Run 1 | Pre: Firestore live. Steps: child → Set up as child (QR shows); parent → Scan child's QR. Expected: parent shows "paired"; both hold the same pairing. | child-side done — "Set up as child" mints a pairing and renders a valid QR on-device. Parent scan + both-hold-same-pairing still needs the 2nd phone.
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-02 | Encrypted upload | P1 | No | Not Run |  | Steps: child enable Share → Sync now. Expected: "Report uploaded ✓"; Firestore reports/{id} has iv+ciphertext blobs only (unreadable), no plaintext fields. | Never device-tested
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-03 | Parent renders decrypted | P1 | No | Not Run |  | Steps: parent opens Remote report after a sync. Expected: per-kid cards (avg, weekly bars, top apps, budget-hit) match the child's stats. | Never device-tested
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-04 | Opt-in OFF = silent | P1 | No | Not Run |  | Steps: leave Share off. Expected: no reports doc is created; nothing uploads. | Never device-tested
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-05 | Cadence reschedule | P1 | No | Not Run |  | Steps: toggle Daily vs Weekly. Expected: the periodic worker's interval updates (inspect via WorkManager/adb). | Never device-tested
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-06 | Key rotation | P1 | No | Not Run |  | Steps: child Rotate key → new QR; old parent tries to view. Expected: old parent can no longer decrypt; re-scanning the new QR works. | Never device-tested
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-07 | Revoke deletes cloud | P1 | No | Not Run |  | Steps: child/parent Stop sharing / unpair. Expected: reports/{id} and commands/{id} deleted from Firestore; local keys wiped; worker cancelled. | Never device-tested
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-08 | Wrong-key state | P1 | No | Not Run |  | Steps: induce a key mismatch (rotate without re-scan). Expected: parent shows "couldn't decrypt", not crash/garbage. | Never device-tested
3 | H. Remote Report ⚠ (P1 — never device-tested) | TC-H-09 | Premium gate | P2 | No | Not Run |  | Pre: promo off, REMOTE_REPORT premium, non-premium. Steps: open child pane. Expected: Share toggle disabled + Plus badge. | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-01 | Remote lock | P1 | No | Not Run |  | Pre: paired; child Allow remote control on. Steps: parent → Lock now. Expected: child locks within a few seconds with an honest lock screen. | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-02 | Grant extra time | P1 | No | Not Run |  | Steps: parent → +30 min. Expected: child's today allowance increases by 30. | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-03 | Set daily limit | P1 | No | Not Run |  | Steps: parent → Set limit 60. Expected: child's daily limit becomes 60 min. | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-04 | Forged command rejected | P1 | No | Not Run |  | Steps: write a commands/{id} doc with ciphertext from a different key. Expected: child ignores it (decrypt fails); no effect. | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-05 | Idempotency | P1 | No | Not Run |  | Steps: deliver a command; restart the child (listener re-attaches and re-reads the doc). Expected: the command applies once, not again. | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-06 | Opt-in OFF | P1 | No | Not Run |  | Steps: child Allow remote control off; parent sends a command. Expected: child ignores it. | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-07 | Parent-face clears remote lock | P1 | No | Not Run |  | Steps: after a remote lock, present the parent face on the child. Expected: lock clears (remote unlock is intentionally not available). | Never device-tested
3 | I. Remote Control ⚠ (P1 — never device-tested) | TC-I-08 | Premium gate | P2 | No | Not Run |  | Pre: promo off, REMOTE_CONTROL premium, non-premium. Steps: child pane + parent controls. Expected: child "Allow remote control" disabled + Plus badge; parent control buttons disabled + Plus badge. | Never device-tested
3 | J. Onboarding, theming & permissions UI (P2) | TC-J-01 | First-run wizard | P2 | No | Not Run |  | Steps: fresh install → launch. Expected: wizard appears; completing/skipping marks first-run done.
3 | J. Onboarding, theming & permissions UI (P2) | TC-J-02 | Tour replay | P2 | No | Not Run |  | Steps: Help → replay welcome/settings tour. Expected: coach marks restart on the right targets.
3 | J. Onboarding, theming & permissions UI (P2) | TC-J-03 | Theme accent | P2 | No | Not Run |  | Steps: Appearance → change accent. Expected: applied immediately + persists across relaunch.
3 | J. Onboarding, theming & permissions UI (P2) | TC-J-04 | Permissions dashboard truth | P1 | No | Not Run |  | Steps: grant/revoke a permission outside the app, return. Expected: dashboard reflects the change; tapping routes to the correct system screen.
3 | K. Permissions & system integration (P1) | TC-K-01 | Usage Access required | P0 | No | Not Run |  | Steps: deny/revoke Usage Access. Expected: app prompts for it; budget/stats clearly need it; no crash.
3 | K. Permissions & system integration (P1) | TC-K-02 | Notifications permission | P1 | No | Not Run |  | Steps: deny POST_NOTIFICATIONS (API 33+). Expected: FGS still runs; app explains the impact.
3 | K. Permissions & system integration (P1) | TC-K-03 | Doze survival | P1 | No | Not Run |  | Steps: leave idle in Doze; trigger a lock later. Expected: service alive; lock works; remote listener reconnects.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-12 | Face enrollment success | P0 | No | Not Run |  | Pre: no face enrolled. Steps: run enrollment in good lighting. Expected: face captured + stored; subsequently unlocks (TC-A-02).
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-13 | Enrollment with no/poor face | P1 | No | Not Run |  | Steps: enroll in darkness / no face in frame. Expected: clear "no face detected" feedback; nothing saved; no crash.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-14 | Protected app opened with NO face enrolled | P1 | No | Not Run |  | Pre: protected app set, but no face enrolled. Steps: open it. Expected: defined behavior (guides to enroll / safe state) — never an unguarded open or a dead lock.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-15 | Re-enroll overwrites | P1 | No | Not Run |  | Steps: enroll a new face over an existing one. Expected: old embedding replaced; old face no longer unlocks; new one does.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-16 | Unlock grace (no immediate re-lock) | P1 | No | Not Run |  | Steps: unlock App X; stay in it / re-open immediately. Expected: not re-prompted while it stays the active unlocked package.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-17 | Re-lock after leaving | P0 | Yes | Partial | Run 3 | Steps: unlock App X, go Home, re-open App X later. Expected: locks again (no permanent unlock). | no-permanent-unlock confirmed — every re-entry of Ludo re-asserts the lock (Home/Back never leave it open). The unlock-then-relock half needs a live face to first authenticate; covered behaviourally by the watchdog re-show (TC-A-09).
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-18 | Camera busy at lock time | P1 | No | Not Run |  | Steps: hold the camera open in another app, trigger a lock. Expected: lock still shows; auth recovers when the camera frees; no crash.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-19 | Auth give-up / retry | P2 | No | Not Run |  | Steps: present nothing for an extended time. Expected: sensible behavior (keeps trying / stays locked); no battery/heat runaway.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-20 | Split-screen / multi-window | P2 | No | Not Run |  | Steps: open a protected app in split-screen. Expected: lock still enforced.
3B | A. Core lock & **enrollment** (was under-covered) | TC-A-21 | Clear app data → re-enroll | P1 | No | Not Run |  | Steps: clear app data. Expected: face embedding gone; protected apps require re-setup + re-enroll; no crash, no silent open.
3B | B. Kid Mode — **clock & boundary security** | TC-B-12 | Toggle Kid Mode on/off | P1 | No | Not Run |  | Steps: switch owner type kid→parent→kid. Expected: enforcement turns off/on correctly; no stuck lock.
3B | B. Kid Mode — **clock & boundary security** | TC-B-13 | Clock-forward budget cheat | P0 | Attempted | Blocked | Run 3 — needs manual clock | Steps: exhaust budget; the kid sets the device clock past 07:00 to force a reset, then back. Expected: the app does not hand out a free extra day from clock tampering (define + verify the resist/detection behavior). Key parental-control attack vector. | not ADB-automatable — the device clock can't be set without root (su absent; date silently reverts under SELinux). Run manually: Settings → Date & time → off auto → jump past 07:00, then open a controlled app and check it stays locked. (Suspect FAIL: reset keys off DAY_OF_YEAR, no monotonic/anti-tamper guard — worth confirming.)
3B | B. Kid Mode — **clock & boundary security** | TC-B-14 | Clock-backward | P1 | No | Not Run |  | Steps: set the clock backward several hours. Expected: budget/usage stay sane; no negative time, no infinite budget.
3B | B. Kid Mode — **clock & boundary security** | TC-B-15 | DST / 07:00 boundary | P2 | No | Not Run |  | Steps: cross a DST change near 07:00. Expected: budget-day boundary stays correct (DAY_OF_YEAR math).
3B | B. Kid Mode — **clock & boundary security** | TC-B-16 | Grant time while already locked (over budget) | P1 | No | Not Run |  | Steps: over-budget lock active; grant +15. Expected: lock releases / app becomes usable for the new allowance.
3B | B. Kid Mode — **clock & boundary security** | TC-B-17 | Free Play while over budget | P1 | No | Not Run |  | Steps: start Free Play after budget exhausted. Expected: temporary unlock for the session, then re-locks to the over-budget state.
3B | B. Kid Mode — **clock & boundary security** | TC-B-18 | Schedule + night-lock overlap | P2 | No | Not Run |  | Steps: configure overlapping schedule + night windows. Expected: locked in the union; no flicker/conflict.
3B | C. Multi-kid — **migration, grace, hand-off** | TC-C-07 | Single→multi migration | P1 | No | Not Run |  | Steps: enable multi-kid from an existing single-kid setup. Expected: existing config migrates to Profile 1; nothing lost.
3B | C. Multi-kid — **migration, grace, hand-off** | TC-C-08 | Revert multi→single | P1 | No | Not Run |  | Steps: turn multi-kid off. Expected: returns to single-kid behavior; no identity scans; data intact.
3B | C. Multi-kid — **migration, grace, hand-off** | TC-C-09 | Identify grace window | P1 | No | Not Run |  | Steps: identify Kid A, then re-open a controlled app within ~2 min. Expected: keeps A active without a fresh scan.
3B | C. Multi-kid — **migration, grace, hand-off** | TC-C-10 | Hand-off A→B | P1 | No | Not Run |  | Steps: Kid A active, Kid B picks up and opens a controlled app after the grace window. Expected: re-identifies as B; B's budget applies.
3B | C. Multi-kid — **migration, grace, hand-off** | TC-C-11 | No confident match | P1 | No | Not Run |  | Steps: present an unknown face (not either kid, not parent). Expected: tap-to-confirm / stricter profile; never a hard lockout.
3B | C. Multi-kid — **migration, grace, hand-off** | TC-C-12 | Remove a kid / face | P1 | No | Not Run |  | Steps: delete a profile or its face. Expected: that kid no longer identified; remaining kid unaffected.
3B | D. Stats — **empty & uninstalled-app paths** | TC-D-04 | Empty stats | P2 | No | Not Run |  | Steps: fresh install, open Stats before any usage. Expected: clean empty state, no crash, no NaN/blank charts.
3B | D. Stats — **empty & uninstalled-app paths** | TC-D-05 | Uninstalled app in window | P2 | No | Not Run |  | Steps: use an app, uninstall it, open Stats covering that period. Expected: it's omitted gracefully (no crash from unresolved package).
3B | D. Stats — **empty & uninstalled-app paths** | TC-D-06 | Kid with zero sessions | P2 | No | Not Run |  | Steps: open a kid's stats who has no recorded sessions. Expected: zeroed/empty view, no crash.
3B | E. Tamper — **resilience** | TC-E-03 | Disable Device Admin is gated | P1 | No | Not Run |  | Steps: attempt to disable admin. Expected: requires the parent gate (not freely removable by the kid).
3B | E. Tamper — **resilience** | TC-E-04 | Force-stop recovery | P1 | No | Not Run |  | Steps: force-stop the app from system Settings. Expected: service restarts (boot/JobScheduler) and locking resumes within a reasonable time.
3B | E. Tamper — **resilience** | TC-E-05 | Clear app data | P1 | No | Not Run |  | Steps: clear data. Expected: full reset (settings, face, profiles); app re-onboards; no half-state.
3B | E. Tamper — **resilience** | TC-E-06 | Lock own app | P1 | No | Not Run |  | Pre: lock-own-app on. Steps: open Shield. Expected: Shield itself requires the parent face.
3B | E. Tamper — **resilience** | TC-E-07 | Safe Mode (known limitation) | P2 | No | Not Run |  | Steps: boot into Safe Mode. Expected: documented partial — third-party FGS may be suspended; verify it recovers on normal boot (full closure needs Device Owner — out of scope).
3B | F. Monetization — **subscription edge states** | TC-F-09 | PENDING purchase | P1 | No | Not Run |  | Steps: trigger a pending (e.g. slow-payment) purchase. Expected: not premium until it completes; no premium granted on PENDING.
3B | F. Monetization — **subscription edge states** | TC-F-10 | Invalid signature | P1 | No | Not Run |  | Steps: simulate a tampered/invalid purchase signature. Expected: entitlement denied (not premium).
3B | F. Monetization — **subscription edge states** | TC-F-11 | Lapsed-but-cached reconcile | P1 | No | Not Run |  | Steps: cache shows premium; sub has lapsed on Play. Steps: relaunch. Expected: re-query revokes; reverts to free.
3B | F. Monetization — **subscription edge states** | TC-F-12 | Promo countdown | P2 | No | Not Run |  | Pre: free_until_epoch_ms set. Steps: open the early-access screen. Expected: countdown displays (display-only; gating still by promo_active).
3B | F. Monetization — **subscription edge states** | TC-F-13 | Manage-subscription deep link | P2 | No | Not Run |  | Steps: tap manage subscription. Expected: opens Play's subscription management.
3B | F. Monetization — **subscription edge states** | TC-F-14 | Upgrade/downgrade | P2 | No | Not Run |  | Steps: switch monthly↔annual. Expected: Play proration flow; entitlement remains.
3B | F. Monetization — **subscription edge states** | TC-F-15 | Entitlement follows the account | P2 | No | Not Run |  | Steps: sign the premium account into a second device. Expected: premium recognized there too.
3B | G. FCM — **token & tap** | TC-G-02 | Token refresh | P2 | No | Not Run |  | Steps: force a token refresh (clear/reinstall). Expected: onNewToken re-subscribes to all.
3B | G. FCM — **token & tap** | TC-G-03 | Notification tap | P2 | No | Not Run |  | Steps: tap a received notification. Expected: opens the app (no crash).
3B | G. FCM — **token & tap** | TC-G-04 | Delivery while app killed | P2 | No | Not Run |  | Steps: swipe-kill the app; send a broadcast. Expected: notification still shows.
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-10 | Parent Empty state | P1 | No | Not Run |  | Steps: parent opens the report when paired but no doc has synced yet. Expected: "Paired — no report yet" (not error/crash). | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-11 | Parent Refresh | P1 | No | Not Run |  | Steps: child syncs; parent taps Refresh. Expected: re-fetches and updates the render. | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-12 | Multi-kid report | P1 | No | Not Run |  | Pre: child in multi-kid mode. Steps: sync + view. Expected: both kids appear as separate cards. | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-13 | Zero-usage report | P2 | No | Not Run |  | Steps: sync with no usage. Expected: report renders with zeros, no crash. | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-14 | Foreign/blurry QR | P1 | No | Not Run |  | Steps: point the parent scanner at a non-Shield QR / blurry code. Expected: ignored; keeps scanning until a valid pairing QR. | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-15 | Camera denied on parent scan | P1 | No | Not Run |  | Steps: deny camera on the parent. Expected: "grant camera" prompt; no crash; scanning resumes after grant. | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-16 | Re-pair overwrites | P2 | No | Not Run |  | Steps: parent scans a different child's QR. Expected: pairing replaced cleanly. | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-17 | Parent offline opening report | P2 | No | Not Run |  | Steps: parent offline, open report. Expected: cached value or graceful "couldn't reach" — no crash. | Never device-tested
3B | H. Remote Report ⚠ — **parent states & QR/edge** | TC-H-18 | Key rotation mid-view | P2 | No | Not Run |  | Steps: child rotates key while the parent has an old report open; parent Refreshes. Expected: decrypt-failed state until the parent re-scans the new QR. | Never device-tested
3B | I. Remote Control ⚠ — **offline, stale, listener lifecycle** | TC-I-09 | Delivery after reconnect | P1 | No | Not Run |  | Steps: child offline; parent sends Lock now; bring child online. Expected: the listener fires on reconnect and applies it. | Never device-tested
3B | I. Remote Control ⚠ — **offline, stale, listener lifecycle** | TC-I-10 | Stale command ignored | P1 | No | Not Run |  | Steps: deliver a command older than the max age (~6h). Expected: ignored (not applied on a late reconnect). | Never device-tested
3B | I. Remote Control ⚠ — **offline, stale, listener lifecycle** | TC-I-11 | Invalid arg (limit ≤ 0) | P1 | No | Not Run |  | Steps: craft Set-limit 0 / Grant 0. Expected: ignored (no zeroed/negative limit applied). | Never device-tested
3B | I. Remote Control ⚠ — **offline, stale, listener lifecycle** | TC-I-12 | Listener re-attaches on state change | P1 | No | Not Run |  | Steps: toggle child Allow-remote-control off→on, or rotate the key. Expected: listener detaches/re-attaches to the right doc; commands still arrive. | Never device-tested
3B | I. Remote Control ⚠ — **offline, stale, listener lifecycle** | TC-I-13 | Rapid multiple commands | P1 | No | Not Run |  | Steps: parent fires several commands quickly. Expected: latest applies; idempotency prevents double-apply; no race crash. | Never device-tested
3B | I. Remote Control ⚠ — **offline, stale, listener lifecycle** | TC-I-14 | Multi-kid set-limit (global, documented) | P2 | No | Not Run |  | Steps: in multi-kid mode, parent sets a limit. Expected: it sets the global/single limit (per-kid targeting is not built) — confirm this matches the documented limitation. | Never device-tested
3B | I. Remote Control ⚠ — **offline, stale, listener lifecycle** | TC-I-15 | Lock when already locked | P2 | No | Not Run |  | Steps: send Lock now while the child is already locked. Expected: no-op/refresh, no double overlay. | Never device-tested
3B | J. Onboarding — **skip & persistence** | TC-J-05 | Skip wizard | P2 | No | Not Run |  | Steps: skip the first-run wizard. Expected: marked done; app usable; not shown again.
3B | J. Onboarding — **skip & persistence** | TC-J-06 | Theme persists across reboot | P2 | No | Not Run |  | Steps: set accent, reboot. Expected: accent retained.
3B | K. Permissions — **denial paths** | TC-K-04 | All-denied cold start | P1 | No | Not Run |  | Steps: fresh install, deny everything. Expected: app guides through each grant; never crashes; clearly blocks the features that need them.
3B | K. Permissions — **denial paths** | TC-K-05 | "Don't ask again" routing | P1 | No | Not Run |  | Steps: permanently deny a permission. Expected: app routes to system Settings (can't re-prompt directly); explains why.
4 | - | TC-X-01 | Mid-use permission revoke | P1 | No | Not Run |  | Steps: revoke overlay/camera/usage while a lock or scan is active. Expected: graceful fallback; no crash.
4 | - | TC-X-02 | Airplane mode during remote op | P1 | No | Not Run |  | Steps: toggle airplane mode mid sync/command. Expected: operation queues; completes on reconnect. | Never device-tested
4 | - | TC-X-03 | RTL layout | P2 | No | Not Run |  | Steps: set device to an RTL locale. Expected: screens mirror correctly; no clipped text.
4 | - | TC-X-04 | minSdk 24 full pass | P0 | No | Not Run |  | Steps: install on API 24; run core lock + Kid Mode + a remote pair. Expected: installs and works; no crash on hex/crypto/QR paths.
4 | - | TC-X-05 | Combined load | P1 | No | Not Run |  | Steps: 2 kids enrolled + remote report + remote control all active. Expected: identify-session and command listener don't interfere. | Never device-tested
4 | - | TC-X-06 | App upgrade preserves data | P1 | No | Not Run |  | Steps: install build N, configure, install build N+1 (versionCode bump). Expected: settings/profiles/face/pairing survive; no re-onboarding.
4 | - | TC-X-07 | Process death restoration | P1 | No | Not Run |  | Steps: force low-memory / kill the process; reopen. Expected: ViewModel/UI state restores sanely; the service is alive (or restarts); no crash.
4 | - | TC-X-08 | Accessibility (TalkBack) | P2 | No | Not Run |  | Steps: enable TalkBack; navigate lock + main screens. Expected: labels/liveRegions read; the lock state is announced; interactive controls reachable.
4 | - | TC-X-09 | Battery saver / OEM killer | P1 | No | Not Run |  | Steps: enable battery saver + an aggressive OEM task-killer; leave idle, then trigger a lock and a remote command. Expected: service survives or auto-restarts; protection + listener recover.
4 | - | TC-X-10 | Rooted device (known limitation) | P2 | No | Not Run |  | Steps: on a rooted device, attempt to spoof the cached premium flag. Expected: documented limitation — client-side entitlement is spoofable on root (server-side is future); confirm it doesn't crash and behaves as designed.
4 | - | TC-X-11 | Clock tamper across features | P1 | No | Not Run |  | Steps: change the device clock and exercise budget reset, report generatedAt, and command freshness together. Expected: no feature is trivially defeated; timestamps/ordering stay coherent.
5 | - | TC-GATE-01 | Two-phone E2E | P0 | No | Not Run |  | Steps: run TC-H-01..03 + TC-I-01..03 on two real phones. Expected: all PASS. | Never device-tested
5 | - | TC-GATE-02 | Billing lifecycle | P0 | No | Not Run |  | Steps: run TC-F-03..06 on the internal track. Expected: all PASS, no real charge.
5 | - | TC-GATE-03 | Soak | P1 | No | Not Run |  | Steps: use normally for 48h. Expected: no crashes; service persistent; lock reliable.
6 | - | TC-6-01 | No remote-unlock affordance | P2 | No | Not Run |  | Steps: inspect parent controls. Expected: no Unlock button; help text says the parent face clears the lock.
6 | - | TC-6-02 | No phantom push claims | P2 | No | Not Run |  | Steps: inspect remote UI/copy. Expected: no promise of automatic "report ready" alerts.